## Sheet1
Project Name: | Lockers Pvt .Ltd
Scrum team: | Dev,Scrum master,QA,PO etc.
Created by: | Product owner (Manikandan.N)
Epic | User story ID | User Story | Story Points | Sprint | Number of days
Aim to digitalize the products in lockedMe.com | US001 | Display welcome message to the user when application is opened | 5 | 1 | 1
| US002 | List the files in the application in ascending order | 8 | 1 | 2
| US003 | Implementing business level operations and add files into the application | 7 | 2 | 1
| US004 | Delete user specified files from the application | 7 | 2 | 2
| US005 | Search user specified file in the application and navigate function to return to menu | 12 | 3 | 2
| US006 | Close the application. | 3 | 3 | 1